Table of Contents

General Information	2

Project Objective	3

Assumptions	3

Project Scope	4

Project Milestones	4

Impact Statement	5

Roles and Responsibilities	5

Resources	6

Project Risks	7

Success Measurements	7

Signatures	7

A. General Information

A. General Information

## General Information

| Project Title: | Development of a World-Class Network Infrastructure for Thukela District Main Hospital. |  |  |
| --- | --- | --- | --- |
| Brief Project Description: | Implementation of a robust and secure network infrastructure to provide fast and reliable internet connectivity to Thukela District Main Hospital, addressing current IT challenges and supporting efficient hospital operations. |  |  |
| Prepared By: | ProTech Team |  |  |
| Date: | 2024/08/06 | Version: | 1.0 |
| ## Project Objective |  |  |  |

Value Addition: Enhances operational efficiency, improves patient care, and ensures data security. Alignment with Strategic Priorities: Supports the Thukela District Municipality’s goal of improving healthcare services and digital infrastructure. Expected Results: Reliable network connectivity, improved data management, and enhanced security measures. Deliverables: Network design and installation, upgraded IT equipment, security systems, and staff training. Benefits: Improved hospital operations, better patient care, secure data management, and increased staff efficiency. Problems Resolved: Outdated IT infrastructure, missing patient files, and insufficient security measures.

## Assumptions

- Openserve will provide reliable connectivity. - Necessary equipment and resources will be available on time. - Hospital staff will be cooperative and receptive to training. - Budget and timeline will be adhered to without significant delays. - Network installation will be feasible given the hospital's current infrastructure.

## Project Scope

- Design and installation of the network infrastructure. - Implementation of security systems. - Procurement and setup of IT equipment. - Training programs for ICT support and hospital staff.

Excluded from the scope

 Expansion of the network beyond the hospital premises.  Major renovations or structural changes to hospital buildings.

## Project Milestones.

| Milestones | Deliverables | Date |
| --- | --- | --- |
| Project Initiation | Kick-off meeting, Stakeholder engagement | August 15, 2024 |
| Planning | Approved network design, Equipment procurement | September 30, 2024 |
| Implementation | Installed network, Setup IT equipment, Security systems in place | January 31, 2025 |
| Training | Training materials, Completed training sessions | February 28, 2025 |
| Closure | Final testing, Project documentation, Handover | March 31, 2025 |

## Impact Statement

| Potential Impact | Systems / Units Impacted |
| --- | --- |
| Improved Connectivity | Entire hospital network and operations |
| Enhanced Security | Data management systems |
| Upgraded IT Equipment | Hospital wards and offices |
| Staff Training | ICT support staff, Medical and administrative staff |

## Roles and Responsibilities

| Sponsor: Provides overall direction on the project. Responsibilities include: approve the project charter and plan; secure resources for the project; confirm the project’s goals and objectives; keep abreast of major project activities; make decisions on escalated issues; and assist in the resolution of roadblocks. |  |
| --- | --- |
| Name | Email / Phone |
| Project Manager: Leads in the planning and development of the project; manages the project to scope. Responsibilities include: develop the project plan; identify project deliverables; identify risks and develop risk management plan; direct the project resources (team members); scope control and change management; oversee quality assurance of the project management process; maintain all documentation including the project plan; report and forecast project status; resolve conflicts within the project or between cross-functional teams; ensure that the project’s product meets the business objectives; and communicate project status to stakeholders. |  |
| Name | Email / Phone |
| Maduvha M. | ST10191191@rcconnect.edu.za |
| Team Member: Works toward the deliverables of the project. Responsibilities include: understand the work to be completed; complete research, data gathering, analysis, and documentation as outlined in the project plan; inform the project manager of issues, scope changes, and risk and quality concerns; proactively communicate status; and manage expectations. |  |
| Name | Email / Phone |
| Ntsako M. | ST10155751@rcconnect.edu.za |
| Mpho R. | STXXXXX@rcconnect.edu.za |
| Masana M. | ST10211933@rcconnect.edu.za |
| Chuene T. | ST10179994@rcconnect.edu.za |

## Resources

| Resource | Constraints |
| --- | --- |
| Project Budget | R 2,500,000 |
| Network Engineers | R 500,000. |
| IT Support Staff | R 400,000 |
| Training Specialists | R 150,000 |
| Security Experts. | R 300,000 |
| ## Project Risks |  |

| Risk | Mitigation Strategy |
| --- | --- |
| Equipment Delivery Delays | Reliable suppliers, contingency plans |
| Insufficient Staff Training | Multiple training sessions, ongoing support |
| Security Breaches | Robust security protocols, regular audits |
| Staff Resistance | Early stakeholder engagement, emphasize benefits |

## Success Measurements

- Metric: Reliable network connectivity established.

- Target: 100% network uptime, all staff trained, zero security incidents within the first year.

## Signatures

| Customer: |  |  |
| --- | --- | --- |
| Name | Signature | Date |
| Project Sponsors: |  |  |
| Name | Signature | Date |
| Project Manager: |  |  |
| Name | Signature | Date |
| Maduvha M. |  | 2024/08/07 |